KOMENDA EDINA EGUAFO ABREM MUNICIPAL ASSEMBLY

CENTRAL REGION

MONITORING AND EVALUATION

ANNUAL PROGRESS REPORT FOR 2020

JANUARY, 2020

PREPARED BY: MUNICIPAL PLANNING COORDINATING UNIT (MPCU)

Content

INTRODUCTION	3

Core Functions Of The District Assembly	4

Municipal Sub-Structure	5

1.1 STATUS OF IMPLEMENTATION OF DMTDP	5

1.3 PROCESSES INVOLVED AND DIFFICULTIES ENCOUNTERED	7

CHAPTER TWO	9

2.0 M&E ACTIVITIES REPORT	9

2.1 PROJECT STATUS FOR THE YEAR 2020	9

2.2 UPDATE ON DISBURSEMENTS FROM FUNDING SOURCES	24

2.3 Table: 7…..PERFORMANCE OF CORE INDICATORS & TARGETS	25

2.4	UPDATE ON CRITICAL DEVELOPMENT AND POVERTY ISSUES	30

2.4.4 Implementation of Gender Mainstreaming Programmes	33

2.5 EVALUATIONS CONDUCTED; THEIR FINDINGS AND RECOMMENDATIONS	35

2.6 PARTICIPATORY M & E APPROACHES USED AND THE RESULT	36

3.0 THE WAY FORWARD	38

3.1 Key issues addressed and those yet to be addressed	38

# INTRODUCTION

The Komenda- Edina- Eguafo- Abrem Municipality It is made of four Municipal Traditional Areas or States, which have been put together to constitute a political Municipality. Carved out of the Cape Coast Municipal Council, the KEEA Municipality is one of the forty-six (46) new districts created in 1988 as part of the Decentralization Programmes in Ghana.

The Municipality has a fantastic assemblage of culture. Elmina, the Municipal capital, prides itself as the first point of call by the Europeans on their exploration tour of Africa. It had the first contact with the Portuguese in 1471. The oldest Castle in Africa, south of the Sahara, the Elmina Castle, (built by the Portuguese in 1482), is located in the Municipality. The mutual trade relations between the Municipality and its people, (particularly the people of Elmina) and the Dutch span over 300 years.

The Municipality still has the traces of those relationships in terms of architecture, monuments (Dutch Cemetery in Elmina) and European offspring as well as names.

In all, there is one major festival in the municipality which is the Bakatue (Harvest Festival) festival celebrated on the first Tuesday of July by the Elmina Traditional area.

This is a brief profile of the Komenda-Edina-Eguafo-Abrem Municipal Assembly of which Elmina is the Capital. Elmina is one of Ghana’s most famous historic towns and its strategic location and history makes it the beacon for investment and the heart of splendid tourists destination of par excellence not only in the Central Region of Ghana but in the west African sub region.

Figure 1: Geographical Location of the District in the Regional Context

The 2010 PHC report has the Municipal population at 144,705.  The total population for Male is 69,665 and Female is 75,040 representing 48.14% and 51.86% respectively. Thirty-five percent of the population in the Municipality lives in urban centers; the Municipality has an average household size of 4. There are four major towns with respective population figures of over five thousand (5,000) people; these are Elmina, Komenda, Kissi and Agona Abrem.. The projected population of the KEEA Municipality for 2020 is 179,883 which is estimated to increase by 3,958 by the close of 2021

VISION

‘To become a model environment for Local Economic and social development through transparent and participatory local governance’

MISSION

To harness and utilize available resources effectively and efficiently in order to promote sustainable development based on commitment to accountability, quality services, openness, environmental management and active grassroots participation within the confines of good governance.

## Core Functions Of The District Assembly

District Assembly exercises political and administrative authority in the district, provide guidance, give direction to, and supervise the other administrative authorities in the district.

It is responsible for the overall development of the district and shall ensure the preparation and submission through the regional coordinating council, development plans of the district to the National Development Planning Commission for approval and the budget of the district related to the approved plans to the Ministry for Finance for approval;

Additionally, it has the responsibilities to;

- formulate and execute plans, programmes and strategies for the effective mobilization of the resources necessary for the overall development of the district;

- promote and support productive activity and social development in the district and remove any obstacles to initiative and development;

- initiate programmes for the development of basic infrastructure and provide municipal works and services in the district;

- be responsible for the development, improvement and management of human settlements and the environment in the district;

- be responsible in co-operation with the appropriate national and local security agencies, for the maintenance of security and public safety in the district;

- ensure ready access to Courts in the district for the promotion of justice;

Initiate, sponsor or carry out studies that are necessary for the performance of a function conferred by this Act or by any other enactment; and perform any other functions provided for under any other enactment

### Municipal Sub-Structure

In response to the demands for popular participation in promoting decentralization and good governance, the Komenda Edina Eguafo Abrem has been delineated into three (6)  Zonal Councils for easy local level administration.

These include;

- SUB-STRUCTURE

The Assembly has six (6) Zonal Councils namely;

- Komenda Zonal Council

- Elmina Zonal Council

- Ntranoa Zonal Council

- Eguafo Zonal Council

- Ayensudo Zonal Council

- Kissi Zonal Council

## 1.1 STATUS OF IMPLEMENTATION OF DMTDP

The total planned projects and programmes in the 2020 Composite Annual Action Plan of the Assembly is Ninety-Four (94) comprising 26 physical projects including rolled over projects from previous years and 68 non-physical projects.

Overall, 72 projects & programmes representing 77% of planned projects were completed. Projects/Programmes that were commenced but not completed as at 31st December, 2020 are 7 in number. This represents 7% of the total planned projects. The remaining 15 projects/programmes representing 7% were projects as at 31st December,2020 were not implemented and expected to roll over for implementation in 2021. There are no abandoned projects as at 31st December, 2020.

The level of implementation of planned projects/activities as at 31st December, 2020 is illustrated in figure 2 below.

Table 1: PROPORTION OF THE DMTDP IMPLEMENTED IN 2020

|  | Baseline |  | Target | Actual |
| --- | --- | --- | --- | --- |
|  | 2018 | 2019 | 2020 | 2020 |
| 1. Proportion of the annual action plans implemented by the end of the year: |  |  |  | 84% |
| - Percentage completed | 64% | 72.66% | 80% | 77% |
| - Percentage of ongoing interventions | 11% | 2.34% | 0% | 7% |
| - Percentage of interventions abandoned | 0% | - | 0% | 0% |
| - Percentage of interventions yet to start | 25% | 25% | 0% | 16% |
| 2. Proportion of the overall medium-term development plan implemented | 18.75 | 21.08% | 25% | 21% |

Table 2: Details on the annual action plan implemented under the Agenda for Jobs Policy Framework

| Sn | Development dimension | 2020 |  |
| --- | --- | --- | --- |
|  |  | Plan | Exec. |
| 1. | Economic Development | 10 | 8- Completed 1- Ongoing 0- Abandoned 1- Yet To Start |
| 2. | Social Development | 35 | 25- Completed 2- Ongoing 0- Abandoned 8- Yet To Start |
| 3. | Environment, infrastructure and Human Settlement | 20 | 15- Completed 3- Ongoing 0- Abandoned 2- Yet To Start |
| 4. | Governance, Corruption and Accountability | 29 | 24- Completed 1- Ongoing 0- Abandoned 4- Yet To Start |
| 5. | Ghana’s role in international affairs | 0 | 0 |
|  | Total | 94 | 72-Completed 7- Ongoing 0- Abandoned 15- Yet to start |

1.2 PURPOSE OF THE M&E FOR THE STATED PERIOD

The essence of the M&E for the period under review is to track the level of implementation of programmes and projects in the District Composite Annual Action Plan and by extension the District Medium Term Development Plan. This is also in fulfilment of the mandate of the District Planning Coordinating Unit (DPCU) under the LI 2232 and the Local Governance Act, 2016 (Act 936) to submit to the appropriate quarters, report on the progress of all programmes and projects being implemented in the District.

## 1.3 PROCESSES INVOLVED AND DIFFICULTIES ENCOUNTERED

Relevant data on activities outlined for the year was collected from the departments and stakeholders including development agencies operating in the district using participatory approaches, project and programme reviews as tools. The Municipal Planning and Coordinating Unit undertook the collation and analysis of the data. The results of the analysis were then validated and disseminated at stakeholders’ review forum organized at the district capital.

The Planning Unit has great challenge of getting no or timely furnishing of data from the Departments/Unit hence the inability of completing the 20 District Core Indicators. Another challenge is the inadequacy of logistics for monitoring and evaluation.

The Planning Unit has great challenge of getting no or timely furnishing of data from the Departments/Unit hence the inability of completing the 20 District Core Indicators. Another challenge is the inadequacy of logistics for monitoring and evaluation.

## CHAPTER TWO

# 2.0 M&E ACTIVITIES REPORT

## 2.1 PROJECT STATUS FOR THE YEAR 2020

Table 3: Project Register for 2020

| s/n | PROJECT DESCRIPTION | DEVELOPMENT DIMENSION | LOCATION | CONTRACTOR/CONSULTANT |  | CONTRACT SUM GH ₵ | SOURCE OF FUNDING | DATE OF AWARD | STARTING DATE | EXSPECTED DATE OF COMPLETION | EXPENDITURE TO DATE | OUTSTANDING BALANCE | IMPLEMENTATION STATUS (%) | REMARK |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Construction of Reinforced concrete foot bridge at Komenda-Amotuo | Environment, infrastructure and human settlement | Komenda | Gyprons Construction Ltd |  | 69,159.30 | DACF-RFG | 04/09/19 | 16//10/19 | 31/12/19 | 65,698.2 | 3,461.10 | 100% | Completed |
| 2 | Construction of 1no. 32-unit market stalls and 4-seater toilet facility at Ayensudo Fruits Market | Economic Development | Ayensudo | Axiles Construction Works |  | 270, 401.45 | DACF-RFG | 04/09/19 | 16/10/19 | 28/02/20 | 249,402.80 | 20,998.65 | 95% | On going |
| 3 | Redevelopment of Agona Market | Economic Development | Agona | Rekadon Enterprise |  | 548,587.00 | DACF-RFG | 04/09/19 | 16/10/19 | 28/02/20 | 544,906 | 3,680.33 | 100% | Completed |
| 4 | Construction of Market Shed at Elmina Fish Market | Economic Development | Elmina | Axiles Construction Works |  | 61,750.00 | DDF | 04/09/19 | 19/09/19 | 30/12/19 | 55,575.00 | 6,175.00 | 100% | Completed |
| 5 | Development of new final Disposal site | Environment, infrastructure and human settlement | Aboransa | Kofamp Ventures |  | 35,000.00 | DACF | 25/11/19 | 02/12/2019 | 30/03/2020 | 35,000.00 | 0 | 100% | Completed |
| 6 | Reshaping and filling of Komenda Junction lorry park | Environment, infrastructure and human settlement | Komenda | Kofamp Ventures |  | 45,000.00 | DACF | 17/12/19 | 17/12/20 | 6/01/20 | 45,000.00 | 0 | 100% | Completed |
| 7 | Construction of 1no. 2-unit CRB with office and store room | Social development | Kwesi Adum | Theometro construction Ltd |  | 129,183.08 | DDF | 11/12/2017 | 5/3/18 | 31/10/18 | 113,528.48 | 15,654.60 | 100% | Completed |
| 8 | Construction of lorry terminal at Elmina Junction | Environment, infrastructure and human settlement | Elmina | Kwas Construction Works |  | 47,300.00 | DACF | 17/12/19 | 6/01/20 | 6/01/20 | 47,300.00 | 0 | 100% | Completed |
| 9 | Renovation of Education Director’s bungalow | Environment, infrastructure and human settlement | Elmina | Jaycee Company Ltd |  | 25,391.30 | DACF | 21/11/19 | 21/11/19 | 22/02/20 | 25,391.30 | 0 | 100% | Completed |
| 10 | Renovation of holding cells and external washrooms of Elmina Magistrate Court | Environment, infrastructure and human settlement | Elmina | Kofamp Ventures |  | 18,366.20 | DACF | 21/11/19 | 12/12/19 | 12/12/19 | 18,366.20 | 0 | 100% | Completed |
| 11 | Erection of overhead tank and water connection to six (6) markets and one (1) lorry park | Social development | Elmina, Komenda, Kissi, Agona, Ayensudo, Mpoben | Odum-Amafu Construction Works |  | 130,193,65 | DACF-RFG | 07/05/20 | 12/05/20 | 12/05/20 | 123,013 | 7,180.65 | 100% | Completed |
| 12 | Paving, Landscaping and Fencing of Open Space at Komenda | Environment, infrastructure and human settlement | Komenda | Edjeffdanson Enterprise Ltd |  | 139,750.00 | DACF-RFG | 07/05/20 | 12/05/20 | 07/07/20 | 48,433.93 | 91,316.07 | 100% | Completed |
| 13 | Renovation of planning and budget flats | Governance & Social Accountabilty | Elmina-Marine | Fine Job |  | 81,569.00 | DACF | 08/06/20 | 15/06/20 | 09/09/20 | 81,569.00 | 0 | 100% | Completed |
| 14 | Renovation of MCE’s residence | Governance & Social Accountabilty | Elmina-Marine | Kofamp Ventures |  | 50,000.00 | DACF | 02/04/20 | 17/04/20 | 12/06/20 | 50,000.00 | 0 | 100% | Completed |
| 15 | Construction of 3No. KG blocks and 1No. 3-Unit classroom bock | Social development | . Kwesi Adum 2. Duakyimase 3. Sehwi 4. Kissi | Kwas Construction Works, Theometro construction Ltd, Edjeffdanson Enterprise Ltd |  | 573,926.96 | DACF-RFG | 06/03/20, 12/05/20,07/08/20 | 14/03/20, 25/25/20, 30/18/20 | 20/09/20,22/10/20,30/11/20 | 573,926.96 | 0 | 100% | Completed |
| 16 | Completion of 2 No. 6 unit classroom Block with library, store, | Social development | . Ayensudo 2. Akwakrom | Fine Job |  | 81,988.92 | DACF | 03/06/19,14/09/19 | 13/06/25,14/09/19 | 17/09/25,14/12/19 | 81,988.92 | 0 | 100% | Completed |
| 17 | Construction and furnishing of 2No. CHPS Compounds with external works | Social development | Eguafo 2. Saman Abotar Park | Kofamp Ventures |  | 399,030.00 | DACF-RFG | 18/07/20 13/04/20 | 29/07/20 19/04/20 | 18/11/20 13/08/20 | 399,030.00 | 0 | 100% | Completed |
| 18 | Renovation of Health Director’s Bungalow and reconstruction, of fence | Social development | Elmina | Theometro construction Ltd, |  | 40,000.00 | DACF | 08/03/20 | 20/10/20 | 19/05/20 | 40,000.00 | 0 | 100% | Completed |
| 19 | Completion of 2No. CHPS Compound | Social development | Nsadwir Akwanda | Jaycee Company Ltd |  | 29,857.69 | DACF | 12/03/19 13/04/19 | 12/03/19 15/04/19 | 13/06/19 15/07/19 | 29,857.69 | 0 | 100% | Completed |
| 20 | Completion of Elmina Urban Health Center | Social development | Elmina | Fine Job |  | 55,000.00 | DACF-RFG |  |  |  | 55,000.00 | 0 | 100% | Completed |
| 21 | Construction of Market sheds at Dominase | Economic Development | Dominase | Kofamp Ventures |  | 17,389.26 | DACF-RFG | 09/04/20 | 18/04/20 | 20/08/20 | 17,389.26 | 0 | 100% | Completed |
| 22 | Patching of potholes, Blading and Reshaping of feeder roads | Economic Development | Eguafo – Ponkrom (11KM), Essaman-Bantama-Pershie (5.36KM), Ayensudo Jnc.-Anpenyi Township (6.23KM), Agona – Saman Abotar Park (10KM) |  | Odum-Amafu Construction Works | 94,838.26 | DACF | 08/07/20 | 19/07/20 | 20/11/20 | 94,838.26 | 0 | 100% | Completed |

Table 4: Programme Register for 2020

| PROGRAMME DESCRIPTION | DEV’T DIMENSION | TOTAL BUDGET GHC | DATE STARTED | EXPECTED DATE OF COMPLETION | EXPENDITURE TO DATE | OUTSTANDING BALANCE | IMPLEMENTATION STATUS (%) | TOTAL BENEFECIARIES | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Training on Performance Management | Governance, Corruption & Accountability | 5,859.00 | 3/02/2020 | 9/04/2020 | 5,859.00 | 0 | 100 | MALE - 93 FEMALE – 87 | Completed |
| Preparation of 2021 Annual Action Plan and MPCU meetings | Governance, Corruption & Accountability | 12,000.00 | 17/01/2020 | 29/05/2020 | 12,000.00 | 0 | 100 | - | Prepared and approved |
| Preparation of Composite Budget (FFR for 2021) | Governance, Corruption & Accountability | 25,931.00 | 09/01/2020 | 20/05/2020 | 25,931.00 | 0 | 100 | - | Prepared and approved |
| Budget Dissemination | Governance, Corruption & Accountability | 11,349.66 | 29/05/2020 | 29/06/2020 | 11,349.66 | 0 | 100 | MALE - 57 FEMALE - 71 | Completed |
| Social Accountability and Town Hall forums | Governance, Corruption & Accountability | 18,325.51 | 13/03/2020 24/09/2020 | 20/03/2020 1/10/2020 | 18,325.51 | 0 | 100 | MALE - 107 FEMALE - 330 | Two THMs Held |
| Building and Updating of Socio Economic & Revenue Data for Planning and Budgeting | Economic Development | 25,000.00 | 6/02/2020 | 31/12/2020 | 2,000.00 | 0 | 10 | - | On-going |
| Propagation, Planting and replacement of Flowers and trees within KEEA | Environment, infrastructure and human settlement | 15,000.00 | 26/02/2020 | 18/10/2020 | 15,000.00 | 0 | 100 | MALE FEMALE | Completed |
| Street Naming and Property Addressing | Environment, infrastructure and human settlement | 9,900.00 | 15/02/2020 | 10/12/2020 | 2,000.00 | 7,900.00 | 40% | - | On-going |
| Support for annual Best Teachers Award and sports and culture | Social development | 17,688.15 | - | - | 17,688.15 | 0 | 100 | MALE FEMALE | Completed |
| Support for the organization of BECE Mock exams | Social development | 60,000.00 | - | - | 60,000.00 | 0 | 100 | - | Completed |
| National Immunization Day support | Social development | 10,000.00 | - | - | 10,000.00 | 0 | 100 | MALE FEMALE | Completed |
| Support for Malaria Prevention & other Health activities within the Municipality (0.5%). | Social development | 17,507.55 | - | - | 17,507.55 | 0 | 100 | - | Completed |
| Maintenance of Law and Order in the Municipality | Social development | 27,000.00 | - | - | 27,000.00 | 0 | 100 | - | Ongoing |
| Procurement of Office Equipment Machines & Consumables |  | 40,292.27 | - | - | 40,292.27 | 0 | 100 | - | Completed |
| Monitor external factors affecting the performance of crop and livestock production (e.g. flooding, sand winning, pest and disease attacks, etc.) | Economic Development | 28,000.00 | 16/01/2020 | 31/12/2020 | 28,000.00 | 0 | 100 | - | Recurrent |
| Introduction of new cultivars that are drought and heat tolerant | Economic Development | 50,000.00 | 17/02/2020 | 4/12/2020 | 50,000.00 | 0 | 100 | MALE – 780 FEMALE - 370 |  |
| Sensitization of farming communities on agricultural diversification (including animal rearing as adaptation measure against the effect of climate change and as source of income | Economic Development | 37,000.00 | 25/11/2020 | 30/12/2020 | 37,000.00 | 0 | 100 | MALE – 959 FEMALE – 597 | Sensitization Done |
| Sanitation and Waste Management at the Local level | Environment, infrastructure and human settlement | 89,000.00 | 13/11/2020 | 30/12/2020 | 89,000.00 | 0 | 100 | - | Fully implemented for the year |
| Implement CLTS and monitoring of triggered Communities Under CLTS programme | Environment, infrastructure and human settlement | 25,000.00 | 28/02/2020 | 31/12/200 | 25,000.00 | 0 | 100 | - | Monitoring done in triggered communities and households |
| Inspection and Monitoring of Public Toilet Operations and Maintenance | Environment, infrastructure and human settlement | 1,800.00 | 22/09/2020 | 30/12/2020 | 1,800.00 | 0 | 100 | - |  |
| Operation and maintenance of office activities |  | 17,700.00 | 3/09/2020 | 31/12/2020 | 17000.00 | 0 | 100 | - | Recurrent |
| Marketing and Promotion of Clean environment in the Municipality | Environment, infrastructure and human settlement | 50,000.00 | 31/01/2020 | 30/09/2020 | 50,000.00 | 0 | 100 | - | Completed for the year |
| Undertake Behavioral change communication campaign | Environment, infrastructure and human settlement | 15,000.00 | 20/01/2020 | 31/03/2020 | 15,000.00 | 0 | 100 | - | Completed for the year |
| Sister City and VNG programs | Environment, infrastructure and human settlement | 60,000.00 | 02/03/2020 | 31/11/2020 | 60,000.00 | 0 | 100 | - | Completed for the year |
| Disaster and Contingency | Environment, infrastructure and human settlement | 351,709.98 | 02/03/2020 | 31/12/2020 | 351,709.98 | 0 | 100 | - | Completed for the year |
| Organization of public forum on climate change and disaster risk reduction | Environment, infrastructure and human settlement | 5,000.00 | 29/07/2020 | 31/12/2020 | 5,000.00 | 0 | 100 | MALE FEMALE | Sensitization done |
| Procurement of 6No. Refuse Containers for six communities | Environment, infrastructure and human settlement | 51,000.00 | - | - | 51,000.00 | 0 | 100 | - | Not done |
| Sanitation Improvement Package and fumigation | Environment, infrastructure and human settlement | 414,000.00 | 02/01/2020 | 03/02/2020 | 414,000.00 | 0 | 100 | - | Completed |
| Enforcement of Laws, Enacting and Gazetting of Anti-Dumping Laws | Environment, infrastructure and human settlement | 10,000.00 | 02/01/2020 | 29/01/2020 | 10,000.00 | 0 | 100 | - | Completed |
| Training of Child protection actors | Social development | 6,400.00 | 08/10/2020 | 13/12/2020 | 6,400.00 | 0 | 100 | MALE= 19 FEMALE = 16 | Completed |
| Leadership Skills training for 5No. women’s groups | Social development | 5,000.00 | 4/11/2020 | 30/12/2020 | 5,000.00 | 0 | 100 | FEMALE - 25 | Training completed |
| Basic human rights and advocacy training programme for 5No. women groups and 3No. men’s groups | Social development | 5,077.21 | 20/02/2020 | 22/10/2020 | 5,077.21 | 0 | 100 | MALE – 15 FEMALE – 25 | Training completed |
| Monitoring and evaluation of projects | Governance, Corruption & Accountability | 48,763.00 | 2/03/2020 | 20/12/2020 | 68,763.76 | 0 | 100 | - | Completed |
| Farmer’s day celebration |  | 35,000.00 | 7/12/2020 | 8/12/2020 | 35,000.00 | 0 | 100 | - | Completed |
| Planting for food and jobs and PERD activities | Economic Development | 100,000.00 | 14/02/2020 | 31/12/2020 | refer |  |  | Refer | Ongoing |
| Support to tourism Development sports and culture | Economic Development | 40,132.82 | - | - | 40,132.82 | 0 | 100 | - | Completed for the year |
| Municipal Education Sponsorship | Social Development | 70,020.21 | - | - | 70,020.21 | 0 | 100 | MALE – 47 FEMALE – 27 |  |
| Property valuation | Environment, infrastructure and human settlement | 50, 000.00 | 1/3/2020 | 23/03/2020 |  |  | 3 |  | On-going |
| Sensitization of pupils on sexual and reproductive health | Social Development | 35,200.00 | 4/03/2020 | 14/11/2020 | 35,200.00 | 0 | 100 | MALE – 319 FEMALE – 411 | Completed |
| Procurement of economic enhancement items for PWDs | Social Development | 73, 130.21 | - | - | 73, 130.21 | 0 | 100 | MALE – FEMALE – | completed |
| Implementation of national anti-corruption action plan for 2021 | Social Development | 3,500.00 | 30/09/2020 | 31/12/2020 | 3,500.00 |  | 50% |  | On-going |
| Training of revenue collectors and capacity building of staff | Economic |  | 21/02/2020 | 20/03/2020 | 23,000.00 |  |  |  | Completed |
| Capacity building of staff and assembly members | Social Development |  | 26/02/2020 | 1/04/2020 | 34,615.00 |  | 100% |  | Completed |
| Support to one district one factory project | Economic | 61,749.00 | 6/01/2020 | 31/12/2020 |  |  | 100% |  | Completed |
| Valuation of selected properties | Environment, infrastructure and human settlement | 50,000.00 | 2/12/2020 | 31/12/2020 |  |  | 10% |  | 0n-going |
| Procurement of building materials for minor maintenance within the assembly | Environment, infrastructure and human settlement | 42,601.74 | 30/09/2020 | 30/12/2020 |  |  | 100% |  | Completed |
| Production of site plans, drawings and registration of assembly lands | Environment, infrastructure and human settlement | 47,253,71 | 17/01/2020 | 1/04/2020 |  |  | 100% |  | Completed |
| Production of cadastral maps for forest reserves | Environment, infrastructure and human settlement | 31,066.59 | 17/01/2020 | 1/04/2020 |  |  | 20% |  | On-going |
| Disaster management | Environment, infrastructure and human settlement | 38,149.86 | 22/09/2020 | 31/12/2020 |  |  | 100% |  | Completed |
| Undertake education programmes in the communities on social issues (E.g. child trafficking) | Social Development | 9,850.00 | 5/02/2020 | 5/03/2020 |  |  | 100% |  | Completed |
| Promote and sustain pro-programmes for vulnerable in the municipality | Social Development | 10,150.00 | 21/02/2020 | 21/05/2020 | 10,150.00 | - | 100% |  | Completed |
| Sustain all child rights promotion and protection programmes | Social Development | 9,850.00 | 10/03/2020 | 22/06/2020 | 9,850.00 | - | 100% |  | Completed |
| Build financial capacity of women in skills acquisition | Social Development | 30,000.00 | 18/12/2020 | 31/12/2020 | 30,000.00 | - | 100% |  | Completed |
| Promote and sustain pro-programmes for vulnerable in the municipality | Social Development | 10,150.00 | 1/01/2020 | 31/03/2020 | 10,150.00 | - | 100% |  | Completed |
| Training market leaders and women business owners on market skills and meeting tax obligations | Social Development | 35,000.00 | 21/12/2020 | 31/12/2020 | 35,000.00 | - | 100% |  | Completed |
| Tax education programmes | Social Development | 35,000.00 | 14/03/2020 | 15/06/2020 | 35,000.00 | - | 100% |  | Completed |
| Conduct Multi-Round Annual Crop and Livestock Survey (MRACLS) | Economic | 8,400.00 | 01/02/2020 | 31/12/2020 | 7,470.00 | 930.00 | 95 | 20 |  |
| Monitoring of activity implementation by MCE, MCD, MDA, MAOs and Accountant | Economic | 24,000.00 | 02/01/2020 | 31/12/2020 | 24,000.00 | 0.00 | 100 |  |  |
| Collection of commodities and farm inputs prices | Economic | 3,600.00 | 02/01/2020 | 31/12/2020 | 3,600.00 | 0.00 | 100 | 576 |  |
| Periodic performance assessment and monitor positive changes in socio-economic status of beneficiaries | Economic | 2,954.00 | 15/03/2020 | 31/12/2020 | 800.00 | 2,154.00 | 80 |  |  |
| Facilitate distribution of 14,300 coconut seedlings to 200 farmers | Economic | 101,260.00 | 01/02/2020 | 30/09/2020 | 90,260.00 | 11,000.00 | 100 | Male – 232 Females – 48 Institutions – 2 Total = 282 | A total of 20,000 coconut seedlings were distributed to farmers |
| Organise sensitization sessions on PERD and PFJ for 500 farmers | Economic | 1,600.00 | 02/02/2020 | 30/11/2020 | 1,600.00 | 0.00 | 100 | Male – 2,246 Females – 1,520 Total = 3,766 |  |
| Facilitate establishment of 2,500 acres and 120 acres of maize and vegetables respectively | Economic | 2,200.00 | 02/02/2020 | 30/11/2020 | 2,200.00 | 0.00 | 100.00 | Male – 2,259 Females – 1,233 Institutions – 9 Total = 3,501 | A total of 17,878 kg and 7 kg of seed maize and vegetable seeds were distributed |
| Six Officers record the sale of distribution of farm inputs under PFJ | Economic | 3,600.00 | 02/02/2020 | 30/11/2020 | 3,600.00 | 0.00 | 100.00 |  |  |
| Establish one livestock demonstration centre with prototypes of various livestock housing | Economic | 2,440.00 | 01/04/2020 | 31/07/2020 | 2,440.00 | 0.00 | 100.00 |  |  |
| Establish 16 demonstration plots on maize-cowpea strip as climate smart and conservation agriculture strategy | Economic | 4,850.00 | 01/02/2020 | 30/11/2020 | 4,850.00 | 0.00 | 100.00 | Male – 104 Females – 78 Total = 182 |  |
| Organize a Farmer Business School for 100 farmers | Economic | 810.00 | 01/02/2020 | 30/11/2020 | 0.00 | 810.00 | 0.00 |  |  |
| Conduct 2 field days for 50 farmers to the Livestock Demonstration Centre to increase adoption of construction of improved housing structures for animals | Economic | 1,520.00 | 01/07/2020 | 30/11/2020 | 1.520.00 | 0.00 | 100.00 | Male – 24 Females – 26 Total = 50 |  |
| Organise 3 training and demonstration sessions on safe handling of agro-chemicals for 75 youth and women in dry-season vegetable production | Economic | 1,175.00 | 01/04/2020 | 30/09/2020 | 1,175.00 | 0.00 | 100.00 | Male – 74 Females – 14 Total = 89 |  |
| Organise 2 training and establish demonstration sessions on feed formulation and safety, production of quality broiler meat and eggs; and business management for 50 poultry farmers | Economic | 1,530.00 | 01/04/2020 | 30/09/2020 | 0.00 | 1,530.00 | 0.00 |  |  |
| Organiz 18 FM Radio Programmes at Benya FM station throughout the year. | Economic | 5,040.00 | 02/01/2020 | 31/12/2020 | 5,040.00 | 0.00 | 100.00 |  |  |
| Sensitize 300 farmers on HIV/AIDS and Child Labour impacts on agricultural performance in the municipality | Economic | 2,220.00 | 01/04/2020 | 31/12/2020 | 2,220.00 | 0.00 | 100.00 | Male – 92 Females – 208 Total =300 |  |
| Aquaculture awareness creation through community engagements, radio talk shows, workshops and field demonstrations for farmers | Economic | 1,465.00 | 02/01/2020 | 31/12/2020 | 1,465.00 | 0.00 | 100.00 | Male – 40 Females – 35 Total =75 |  |
| Strengthen 5 FBOs in group dynamics, building a strong team, preventing and managing Conflict, records keeping and create the awareness of credit facilities available to help their work | Economic | 1,682.00 | 01/02/2020 | 30/09/2020 | 1,682.00 | 0.00 | 100.00 | Male – 48 Females – 105 Total =153 |  |
| Train 5 FBOs in pineapple, citrus and watermelon production on GAPs and link them to Peterfield and Ray Processing Company Limited, facilitate the signing of MOU to enhance market opportunities | Economic | 3,160.00 | 01/02/2020 | 30/09/2020 | 0.00 | 3,160.00 | 0.00 |  |  |
| Support the running of District Centre for Agriculture, Commerce and Technology (DCACT) activities - provide information materials on DCACT | Economic | 2,700.00 | 02/01/2020 | 30/06/2020 | 2,700.00 | 0.00 | 100.00 |  |  |
| Train 120 market women and food vendors on food handling and safety in 4 communities by June 2020 | Economic | 1,200.00 | 02/01/2020 | 31/03/2020 | 1,200.00 | 0.00 | 100.00 | Male – 12 Females – 166 Total =178 |  |
| Supply of Orange Fleshed Sweet Potato (OFSP) vines to 100 women to promote sale and consumption of OFSP; and enhance their nutritional status | Economic | 1,228.00 | 02/07/2020 | 31/09/2020 | 0.00 | 1,228.00 | 0.00 |  |  |
| Undertake PPR Vaccination for 900 small ruminants in 8 communities | Economic | 2,860.00 | 02/07/2020 | 31/09/2020 | 0.00 | 2,860.00 | 0.00 |  |  |
| Undertake clinical interventions and treatment of livestock species | Economic | 7,800.00 | 02/01/2020 | 31/12/2020 | 7,800.00 | 0.00 | 100.00 |  |  |
| Conduct disease surveillance in both domestic and wild animals | Economic | 740.00 | 01/01/2020 | 31/12/2020 | 0.00 | 740.00 | 100.00 |  |  |
| Sixteen Agricultural Extension Agents and NABCo personnel to undertake 3,072 farm and home visits to farmers and farm families to educate them on Good Agricultural Practices and emerging issues (climate change mitigation and adaptation measures, HIV/AIDS, child labour, etc.) | Economic | 27,600.00 | 02/01/2020 | 31/12/2020 | 27600.00 | 0.00 | 100.00 | Male – 7,119 Females – 4,804 Total =11,923 |  |
| Conduct Research-Extension-Farmer-Linkage Committee (RELC) Planning and Review Session for 25 Agricultural Officers and 35 actors along the value chain | Economic | 3,410.00 | 01/04/2020 | 30/06/2020 | 3,410.00 | 0.00 | 100.00 | 35 actors and 25 technical officers participated |  |
| Organise 1 exhibition (mini fair) to promote sale consumptio of Orange Fleshed Sweetpotato, rabbits and food innovation | Economic | 1,524.46 | 01/11/2020 | 31/12/2020 | 1,524.46 | 0.00 | 100.00 | 300 people participated |  |
| Organise the municpal version of the National Farmers' and Fishermen's Day Celebration | Economic | 40,000.00 | 01/09/2020 | 30/11/2020 | 40,000.00 | 0.00 | 100.00 | Twelve (12) individual farmers, 1 FBO and 1 institution were awarded |  |
| Organise 2 training sessions and establish 30 demonstration sites on pasture development and support 60 small ruminant farmers in 60 communities to establish pasture in their backyard | Economic | 2,330.00 | 01/04/2020 | 30/09/2020 | 2,330.00 | 0.00 | 100.00 | Sixty (60) farmers trained and supported to establish pasture |  |
| Conduct Multi-Round Annual Crop and Livestock Survey (MRACLS) | Economic | 8,400.00 | 01/02/2020 | 31/12/2020 | 7,470.00 | 930.00 | 95 | 20 |  |

## 2.2 UPDATE ON DISBURSEMENTS FROM FUNDING SOURCES

Table 1:  Financial Sources (Performance)

Table 5: UPDATE ON REVENUE SOURCES

| Expenditure Item | Baseline 2019 | Target/Budget 2020 | Actual 2020 |
| --- | --- | --- | --- |
| IGF | 961,471.87 | 1,315,457.22 | 986,934.94 |
| DACF | 2,633,281.85 | 3,643,276.71 | 263,477.62 |
| MP’s CF | 339,407.68 | 412,000.00 | 321,412.27 |
| PWDs CF | 167,662.82 | 630,000.00 | 300,088.77 |
| MSHAP |  | 20,000.00 | 74,125.50 |
| GSFP |  |  |  |
| SRWSP-IDA |  |  |  |
| DDF | 1,158,393.60 | 1,757,797.72 | 1,011,494.30 |
| GSOP |  |  |  |
| UNFPA |  |  |  |
| UDG |  |  |  |
| LEAP | 337,272 |  |  |
| OTHERS | 38,397.91 | 69,195.56 | 2,644.08 |
| TOTAL | 5,633,705.5 | 7,847,727.21 | 2,960,177.48 |

KEEA Trial Balance, 2020

Table 6: UPDATE ON EXPENDITURE

| Expenditure Item | Baseline 2019 | Target 2020 | Actual 2020 |
| --- | --- | --- | --- |
| Compensation | 2,974,666.40 | 2,697,465.33 | 4,071,785.91 |
| Goods and Service | 2,488,188.74 | 4,240,597.00 | 3,170,502.94 |
| Investment/ Assets | 854,547.44 | 2,335,069.09 | 1,136,006.43 |
| Others | 31,073.81 | 115,175.46 | 728,491.60 |
| TOTAL | 6,354,126.39 | 9,388,306.88 | 9,106,786.88 |

KEEA Trial Balance, 2020

## 2.3 Table: 7…..PERFORMANCE OF CORE INDICATORS & TARGETS

| S/N | Indicator (Categorized by Development Dimension of Agenda for Jobs) |  |  | Baseline | Target |  |  |  | Actual |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2019 | 2020 |  |  |  | 2020 |
| ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |
| 1. | Total output in agricultural production |  |  |  |  |  |  |  |  |
|  | - Maize |  |  | 2.30Mt/Ha | 3.0Mt/Ha |  | 3.1Mt/Ha |  |  |
|  | - Rice (milled) |  |  |  |  |  |  |  |  |
|  | - Millet |  |  |  |  |  |  |  |  |
|  | - Sorghum |  |  |  |  |  |  |  |  |
|  | - Cassava |  |  | 33.20Mt/Ha | 35.0 Mt/Ha |  | 34.6Mt/Ha |  |  |
|  | - Yam |  |  |  |  |  |  |  |  |
|  | - Cocoyam |  |  |  |  |  |  |  |  |  |
|  | - Plantain |  |  | 9.3Mt/Ha | 9.30Mt/Ha |  | 9.6Mt/Ha |  |  |  |
|  | - Groundnut |  |  |  |  |  |  |  |  |  |
|  | - Cowpea |  |  |  |  |  |  |  |  |  |
|  | - Soybean |  |  |  |  |  |  |  |  |  |
|  | - Cocoa |  |  |  |  |  |  |  |  |  |
|  | - Shea butter |  |  |  |  |  |  |  |  |  |
|  | - Oil palm |  |  |  |  |  |  |  |  |  |
|  | - Cashew nut |  |  |  |  |  |  |  |  |  |
|  | - Cotton |  |  |  |  |  |  |  |  |  |
|  | - Cattle (number) |  |  | 2,300 | 2,600 |  | 2,675 |  |  |  |
|  | - Sheep (number) |  |  | 12,636 | 13,000 |  | 14,800 |  |  |  |
|  | - Goat(number) |  |  | 48,773 | 40,00 |  | 54,500 |  |  |  |
|  | - Pig(number) |  |  | 6,950 | 9,000 |  | 8,700 |  |  |  |
|  | - Poultry(number) |  |  | 123,500 | 125,500 |  | 158,166 |  |  |  |
| 2. | Percentage of arable land under cultivation |  |  |  |  |  |  |  |  |  |
| 3. | Number of new industries established (commercial farms and agro-processing) established |  | i)Agriculture, |  |  |  |  |  |  |  |
|  |  |  | ii)Industry, |  |  |  |  |  |  |  |
|  |  |  | ii) Service |  |  |  |  |  |  |  |
| 4. | Number of new jobs created - Agriculture |  |  | 69 | 150 |  | 186 |  |  |  |
|  | Indicator (Categorized by Development Dimension of Agenda for Jobs) |  |  | Baseline | Target |  | Actual |  |  |  |
|  | - Industry |  |  |  |  |  |  |  |  |  |
|  | - Service |  |  |  |  |  |  |  |  |  |
| SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| 5. | Net enrolment rate |  |  |  |  |  |  |  |  |  |
|  | - Kindergarten |  |  | 65.5% | 75% |  |  | 68% |  |  |
|  | - Primary |  |  | 90.2% | 95.0% |  |  | 91.3% |  |  |
|  | - JHS |  |  | 47.7% | 50% |  |  | 49% |  |  |
| 6. | Gender Parity Index - Kindergarten |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 0.97 | 1.00 |  |  | 0.94 |  |  |
|  | - Primary |  |  | 0.95 | 1.00 |  |  | 0.97 |  |  |
|  | - JHS |  |  | 0.96 | 1.00 |  |  | 0.96 |  |  |
|  | - SHS |  |  | 1.23 | 1.00 |  |  | 1.21 |  |  |
| 7. | Completion Rate - Kindergarten |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 94.5% | 98% |  |  | 97.6% |  |  |
|  | - Primary |  |  | 117.6% | 100% |  |  | 106% |  |  |
|  | - JHS |  |  | 85.6% | 90% |  |  | 88% |  |  |
|  | - SHS |  |  | 48.8% | 55% |  |  | 51% |  |  |
| 8. | Number of operational health facilities - CHP Compound |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 17 | 21 |  |  | 17 |  |  |
|  | - Clinic |  |  | 1 | 2 |  |  | 1 |  |  |
|  | - Health Centre |  |  | 3 | 4 |  |  | 3 |  |  |
|  | - Hospital |  |  | 1 | 0 |  |  | 1 |  |  |
| 9. | Proportion of population with valid NHIS card - Total (by sex) |  |  | 46,965 | 70,413 |  |  | 47,697 |  |  |
|  | - Male |  |  | 19,115 | 28,850 |  |  | 18,836 |  |  |
|  | - Female |  |  | 27,850 | 30,850 |  |  | 28,831 |  |  |
|  | - Indigents |  |  | 712 | 2,400 |  |  | 4,981 |  |  |
|  | - Informal |  |  | 14,798 | 19,000 |  |  | 16,232 |  |  |
|  | - Aged |  |  | 3,143 | 4,100 |  |  | 2,562 |  |  |
|  | - Under 18years |  |  | 23,037 | 29,900 |  |  | 18,979 |  |  |
|  | - Pregnant woman |  |  | 3,716 | 4,300 |  |  | 2,679 |  |  |
|  | Indicator (Categorized by Development Dimension of Agenda for Jobs) |  |  | Baseline | Target |  |  | Actual |  |  |
| 10. | Number of births and deaths registered |  |  |  |  |  |  |  |  |  |
|  | - Birth (sex) |  |  |  |  |  |  |  |  |  |
|  | - Male |  |  | 1,589 | 2,800 |  |  | 2,263 |  |  |
|  | - Female |  |  | 1,336 | 3,200 |  |  | 1,797 |  |  |
|  | - Death (sex, age group) |  |  |  |  |  |  |  |  |  |
|  | - Male |  |  | 108 | 250 |  |  | 198 |  |  |
|  | - Female |  |  | 90 | 250 |  |  | 107 |  |  |
| 11. | Percent of population with sustainable access to safe drinking water sources1 |  |  |  |  |  |  |  |  |  |
|  | - District |  |  | 70 | 80 |  |  | 75 |  |  |
|  | - Urban |  |  | 40 | 60 |  |  | 50 |  |  |
|  | - Rural |  |  | 100 | 100 |  |  | 100 |  |  |
| 12. | Proportion of population with access to improved sanitation service |  |  |  |  |  |  |  |  |  |
|  | - District |  |  | 11.63% | 30% |  |  | 13.05% |  |  |
|  | - Urban |  |  | 18.75% | 50% |  |  | 19.6% |  |  |
|  | - Rural |  |  | 4.5% | 20% |  |  | 6.5% |  |  |
| 13. | Maternal mortality ratio (institutional) |  |  | 0/100,000(LB) | 0\100,000(LB) |  |  | 0/100,000(LB) |  |  |
| 14. | Malaria case fatality (institutional) - Sex |  |  |  |  |  |  |  |  |  |
|  | - Male |  |  | 0% | 0% |  |  | 0% |  |  |
|  | - Female |  |  | 0% | 0% |  |  | 0% |  |  |
|  | - Age group |  |  |  |  |  |  |  |  |  |
|  | a)<5yrs Malaria Case fatality |  |  | 0% | 0% |  |  | 0% |  |  |
|  | b) >5yrs Malaria Case fatality |  |  | 0% | 0% |  |  | 0% |  |  |
| 15. | Number of recorded cases of child trafficking and abuse |  |  |  |  |  |  |  |  |  |
|  | - Child trafficking (sex) |  |  | 0 | 0 |  |  | 0 |  |  |
|  | - Male |  |  | 0 | 0 |  |  | 0 |  |  |
|  | - Female |  |  | 0 | 0 |  |  | 0 |  |  |
|  | - Child abuse |  |  | 0 | 0 |  |  | 125 |  |  |
|  | - Male |  |  |  |  |  |  | 58 |  |  |
|  | - Female |  |  |  |  |  |  | 65 |  |  |
| 16. | Percentage of road network in good condition |  |  |  |  |  |  |  |  |  |
|  | Total |  |  | 32.8% | 50% |  |  | Awaiting |  |  |
|  | Urban |  |  | 55% | 65% |  |  | Awaiting |  |  |
|  | Feeder |  |  | 1% | 5% |  |  | Awaiting |  |  |
| 17. | Percentage of communities covered by electricity |  |  |  |  |  |  |  |  |  |
|  | District |  |  | 100% | 100% |  |  | 100% |  |  |
|  | Rural |  |  | 100% | 100% |  |  | 100% |  |  |
|  | Urban |  |  | 100% | 100% |  |  | 100% |  |  |
| 18. | Reported cases of crime |  |  |  |  |  |  |  |  |  |
|  | - Men |  |  | 54 | Reduce baseline figure by 50% |  |  | 45 |  |  |
|  | - Women |  |  |  |  |  |  |  |  |  |
|  | - Children |  |  |  |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  |  |  |  |  |
| 19. | Percentage of annual action plan implemented |  |  | 76% | 80% |  |  | 84% |  |  |
| 20. | Number of communities affected by disaster - Bushfire |  |  | 2 | 4 |  |  | 2 |  |  |
|  | - Floods |  |  | 2 | 5 |  |  | 1 |  |  |
| DISTRICT SPECIFIC INDICATORS |  |  |  |  |  |  |  |  |  |  |
| 21 | NADMO |  |  |  |  |  |  |  |  |  |
|  | - Number of major drains desilted |  |  | 2 |  | 4 |  |  | 1 |  |
|  | - Windstorm |  |  | 1 |  | 0 |  |  | 2 |  |
|  | SOCIAL WELFARE & COMMUNITY DEVELOPMENT |  |  |  |  |  |  |  |  |  |
|  | - Child Maintenance |  |  |  |  | 64 |  |  | 85 |  |
|  | - Family Welfare |  |  |  |  | 7 |  |  | - |  |
|  | - inquiry |  |  |  |  | 2 |  |  | - |  |
|  | - Truancy |  |  |  |  | 1 |  |  | - |  |
|  | - Abandonment |  |  |  |  | 2 |  |  | 3 |  |
|  | - Custody |  |  |  |  | 15 |  |  |  |  |
|  | - Child neglect |  |  |  |  | 2 |  |  | 0 |  |
|  | - Family tracing |  |  |  |  | 2 |  |  | 0 |  |
|  | - Juvenile offence |  |  |  |  | 1 |  |  | 0 |  |
|  | ENVIRONMENTAL HEALTH & SANITATION UNIT |  |  |  |  |  |  |  |  |  |
|  | OPEN DEFECATION FREE (ODF) coverage |  |  | 34.4% |  | 50% |  |  | 41% |  |
| GES |  |  |  |  |  |  |  |  |  |  |
|  | GER | KG |  | 101.3% |  | 100% |  |  | 101.2% |  |
|  |  | PRIMARY |  | 118.5% |  | 105% |  |  | 110.1% |  |
|  |  | JHS |  | 96.1% |  | 100% |  |  | 97.1% |  |
|  |  | SHS |  |  |  |  |  |  |  |  |

| Name of Project / Activity | Beneficiaries |  |  |  |  |  | Achievement (Result from intervention) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Male | Female | Inst | Youth | Aged | PLWD |  |
| PFJ | 2.259 | 1,233 | 9 |  |  |  | A total of 17,878 kg of OPV and 200kg hybrid seed maize, 700 grams of vegetable seeds, 45.1 metric tonnes of NPK and 17..45 metric tonnes urea fertilizers were supplied |
| PERD | 531 | 114 | 4 |  |  |  | 48,480 coconut seedlings were distributed. |
| RFJ | 25 | 25 | - | 12 | 15 | - | 500 cockerels were sold at subsidized price to 50 farmers. |

| AGRIC DEPARTMENT |  |  |  |
| --- | --- | --- | --- |
| Indicators / Number of Activities to be Undertaken | 2020 Target | 2020 Achievement | Status of Work / Remarks |
| Number of irrigation facilities available | 2 | 5 | Smallholder irrigation facilities |
| District Centre for Agriculture, Commerce and Technology established and functioning (Yes / No) | Yes | Yes |  |
| Number of beneficiary farmers under PERD | 200 | 282 |  |
| Number of seed banks / nurseries established under PERD | 1 | 1 |  |
| Number of seedlings supplied to farmers under PERD | 14,300 | 20,000 |  |
| No. of hectares cultivation under PERD | 210 | 294 |  |
| Number of employment generated under PERD (specify gender for farmers and farm hands) | Farmers: Males = 120 Females = 80 Farm hands Males = 180 Females = 120 | Farmers: Male – 232 Females – 48 Farm hands Males = 250 Females = 60 |  |
| Number of Agricultural Extension Agents / Officers at post | 32 | 11 |  |
| Number of Farmer Based Organisations / Groups registered by MMDAs | 35 | 31 |  |
| Amount spent on agriculture activities by MMDAs (from GoG, IGF and donor, etc.) | 369,126.66 | 319,115.95 |  |
| Total amount of funds released to Department of Agriculture for the implementation of Annual Action Plan | 369,126.66 | 319,118.78 |  |
| Level of implementation of agriculture Annual Action Plan. (Count of activities in annual action plan and count of activities implemented) | 46 | 40 |  |

*challenge in getting Data from some Department/Unit, still waiting for respective Dep’t/Unit to furnish the DPCU with the Data gaps and furnish u accordingly

  - UPDATE ON CRITICAL DEVELOPMENT AND POVERTY ISSUES

Table 8: CRITICAL DEVELOPMENT AND POVERTY ISSUES IN 2020

| Critical Development and Poverty Issues | Allocation GHȻ | Actual receipt GHȻ | No of beneficiaries |  |
| --- | --- | --- | --- | --- |
|  |  |  | Targets | Actuals |
| Ghana School Feeding Programme |  |  |  |  |
| Capitation Grant | 74,696.83 | 74,696.83 |  |  |
| National Health Insurance Scheme |  |  |  |  |
| Livelihood Empowerment Against Poverty (LEAP) Programme | 342,932.00 | 342,932.00 | 3,234 | 2,519 |
| National Youth Employment Programme |  |  |  |  |
| One District-One Factory Programme |  |  |  |  |
| One Village-One Dam Programme |  |  |  |  |
| Planting for Food and Jobs Programme | 5,800.00 | 5,800.00 | 2,500 | 3,501 |
| Free SHS Programme |  |  |  |  |
| National Entrepreneurship and Innovation Plan (NEIP) |  |  |  |  |
| Implementation of Infrastructural for Poverty Eradication Programme |  |  |  |  |
| PERD | 101,260.00 | 90,260.00 | 200 | 282 |

2.4.1 Planting for Food and Jobs Campaign

The department in collaboration with the Ministry of Food and Agriculture implemented Government of Ghana’s flagship programme - Planting for Food and Jobs” (PFJ) in the period under review.

Maize (OPV and hybrid) and vegetables (tomato, carrot, cabbage, and pepper) were the commodities selected for the campaign in the KEEA Municipality.

The Department of Agriculture and Shalom Agric. Enterprise took delivery of 398 bags (17,910 kg) of certified Open Pollinated Variety (OPV) seed maize. Out of the total quantity received, 17,878 kg, representing 99.82% was sold to 3,501 farmers, comprising 2,259 males, 1,233 females and 9 institutions. A total of 200kg of hybrid maize was also sold to Komenda College of Education.

A total of 700 grams of vegetables 200g, 100g, 100g, 200g and 100g of tomato, chilli pepper, carrot, cabbage and cucumber respectively supplied to 8 farmers.

A total of 1,804 bags (45.1MT) and 698 bags (17.45MT) of NPK and Urea fertilizers respectively were received and sold to beneficiary farmers.

2.4.2    Planting for Export and Rural Development

The KEEA Municipal Department through the joint efforts by the KEEA Municipal Assembly, Ministry of Local Government and Rural Development and MoFA continued with the implementation of the Planting for Export and Rural Development (PERD) programme which was initiated in 2018.

Under this programme, the Municipal Directorate in collaboration with the KEEA Municipal Assembly selected coconut as cash crop for its cultivation and expansion in the municipality.

The department distributed 20,000 coconut seedlings to 282 farmers, comprising 232 males, 48 females and 2 institutions.

This brings to a total of 48,480 coconut seedlings distributed to 649 farmers, comprising 531 males, 114 females and 4 institutions in 2018, 2019 and 2020

2.4.3 Rearing for Food and Jobs (RFJ) Programme

The livestock industry is an important sub-sector within Ghana’s economy in terms of its contributions to both agricultural value-added and national Gross Domestic Product (GDP). The livestock sub-sectors share averaged 14% of agricultural GDP. Its socio-economic importance in the reduction of rural poverty and as a stabilizing factor of families is well acknowledged. At the household level, livestock plays a critical economic and social role in the lives of commercial and smallholder farm households.

To address the meat deficit, government is implementing the Rearing for Food and Jobs (RFJ) Programme, which seeks to develop a competitive and more efficient livestock industry that increases domestic production, reduces importation of livestock products and contributes to employment generation and improvement of livelihoods of livestock value chain actors and the national economy.

The Komenda Edina Eguafo Abrem (KEEA) Municipality is one of the districts selected for all the three modules of the programmes (pigs, broiler and cockerels) to be implemented in 2020.

During the period under review, the department received 500 cockerels from the supplier and sold at subsidized price to 50 smallholder farmers in the municipality

2.4.4 Social & Vulnerable intervntions

Table 9: 2.4.2 Table 10: Pro- Poor intervention Statistics

| OUTCOMES | INDICATOR | LEAP |  | DACF PWDS |  | FREE NHIS BENEFICIARIES (PWD&LEAP) |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Targeting the vulnerable, Marginalized And the disadvantaged With inclusive programmes Implemented | Social inclusive programmes & beneficiaries | Total amount disbursed (GH₵342,932.00) |  | Total amount disbursed (GH₵ 296,433.77) |  | LEAP |  |
|  |  |  |  |  |  | Male | Female |
|  |  | Male (GH₵119,120.00 | Female (GH₵223,812.00 | Male : 44,500.00 | Female: 51,500.00 | 106 | 240 |
|  |  | Total No. of beneficiaries 2,519 |  | Total No. of beneficiaries 93 |  | PWDs |  |
|  |  |  |  |  |  | Male | Female |
|  |  | Male 875 | Female 1,644 | Male 54 | Female 39 | 72 | 69 |
|  |  | Total No. of LEAP HHs 612 |  | Total No. of PWDs in the District 1,079 |  |  |  |
|  |  | Total No. of LEAP beneficiaries HH in the Municipality 767 HH |  | Male 531 | Female 548 |  |  |
|  |  | Male | Female |  |  |  |  |

2.4.4.1 Community Development Programmes

- Sensitization & Education to Sustain all child rights promotion and protection programme was organized at Elmina where stakeholders participated fully

- A forum of diverse economic groups of women including the vulnerable were trained and capacities built on skill acquisition.

- The Department of Social Welfare & Community development embarked on routine community visit to sensitize community members and Promote and Pro-programmes for Vulnerable in the Municipality

2.4.3 Climate Change and Disaster Risk Reduction

According to the United Nations International Strategy for Disaster Reduction (UNISDR), climate change is increasing the risk of natural disasters, with more extreme weather events, the wet season becoming wetter and the dry season drier. Bush fires and floods have become a common occurrence in the country. This has negative effects on lives, the economy and the environment. The frequency and scale of natural disasters is increasing the need for disaster resilience, particularly prevention and preparedness measures.

Climate change and disaster risk reduction activities that were undertaken in the year under review are:

- Inspect safety and protective apparatus used were inspected in organization, industries, market, shops etc.

- Hazard Mapping done on all 6 Zonal Councils

- Routine Public education on Climate Change on Asafo fm/Ahomka Fm/Benya FM and about 45local information centers

- Celebration of World Disaster day was done through the education of climate change safeguards and awareness at Ahomaka/Benya Fm stations

- The year under Review saw 11 DVG’s formed, inspection of Hazards in the community and preparation and identification of safe haven rescue team and materials

- Propagation, planting and replacement of flowers and trees were done in 8 communities across all the 6 zonal councils.

- Earth drains and culvert were inspected and desilted in major drains district wide

- The year under review witnessed massive engagements of Agricultural Extension Officers with farmers in best Farming practices that protect forest cover.

- Development control was routinely organized by the Physical Planning Department to ensure orderly spatial development

- Public Forum Was Organized On Climate Change And Disaster Risk Reduction At The General Hall Of The Municipal Assembly with huge participation

## 2.4.4 Implementation of Gender Mainstreaming Programmes

The District Assembly ensured all programmes and projects implemented were gender sensitive and conscious. The District Planning Coordinating Unit and the Gender Desk Officer ensure strict adherence to the year 2020 monitored the implementation of the following programmes:

| AGRIC DEPARTMENT Name of programme by type | Date | Beneficiaries |  |
| --- | --- | --- | --- |
|  |  | M | F |
| Training on Multi-Round Annual Crop and Livestock Survey (MRACLS) for MISO and AEAs | 06/01/2020 | 1 | 1 |
| West African Forum on Precision Agriculture (WAFPA) | 10/02/2020 – 11/02/2020 | 6 | 3 |
| Eradication of Child Labour in Agricultural Sector | 15/01/2020 | 1 | 0 |
| Sustainable Soil Fertility Management | 20-21/01/2020 | 2 | 0 |
| FBO Training | 22/01/2020 | 1 | 0 |
| Plantwise – how to diagnose diseases and pests of plants | 17/02/2020 – 21/02/2020 | 1 | 2 |
| Overview of Agricultural Extension Policy and Regulatory Framework | 10/06/2020 | 1 | 1 |
| Farmers and Cooperative Business School | 15th – 17th June, 2020 | 2 | 0 |
| Training of Trainers for Animal Production Officers (endo and ecto-parasites control, biosecurity in livestock and poultry production, supplementary feed, report writing and writing effective success stories) | 23th June, 2020 | 1 | 0 |
| Training workshop on Multi Round Annual Crops and Livestock Survey (MRACLS) | 23/07/2020 | 1 | 0 |
| Training of farmers, food processors and Agric Officers on maize aflatoxin using aflasafe GH02 and improved solar dryers | 29/07/2020 | 1 | 0 |
| Identification and control of pest and disease in pineapple cultivation | 06/08/2020 |  | 1 |
| Aflatoxin management | 10/08/2020 | 2 | 2 |
| Training of AEAs in field diagnosis and management of plant pests | 10 – 14/08/2020 | 2 | 0 |
| Training on Public – Private Partnership | 11/08/2020 | 2 | 0 |
| Post-harvest losses management and aflatoxin management | 13/08/2020 | 19 | 9 |
| Re-orientation for staff | 20/08/2020 | 20 | 9 |
| Training workshop on budgeting and financial reporting | 02/09/2020 | 1 | 1 |
| TRICOT - Sweet potato data collection | 04/09/2020 | 5 | 3 |
| Soil Fertility Management in Smallholder Farms | 08/10/2020 | 12 | 6 |
| Farmer Business School | 15 – 17/10/2020 | 2 | 0 |
| Training of Trainers on Small Ruminant and Rabbit production | 15/12/2020 | 1 | 0 |
| Agenda for TRICOT Project Stakeholder Feedback Meeting | 21/12/2020 | 1 | 0 |

ACTIVITY IMPLEMENTED BY GENDER DESK OFFICER

- The year under review saw the Organisation of 4 Sexual & Gender Based Violence trainings for Queen mothers,Adolescent Girls,Stakeholders,Parents and Teacchers at the General Assembly of the Municipal Assembly

2.4.5 LOCAL ECONOMIC DEVELOPMENT PROGRAMMES

The District Assembly through the active participation of District LED Committee who coordinated the implementation of all local economic interventions in all Departments/Units.

The Assembly through its poverty eradication in the District implemented the following LED programmes.

- Quarterly meetings of LED organized

- Implementation of CIP International Potato Center (CIP) in the Municipality

- The Far Dwuma Nkodo Project is implemented by Environmental Justice Foundation and Hen Mpoano with funding from the European Union to help build the capacity of fishing communities in the sustainable management of their resources.

- Implementation of piggery, Cassava & poultry projects at Egyeikrom refugee camp under the UNHCR/ADRA Projects

- Organized 4 Quarter meetings of District LED Committee

- Two 2 training sessions were organized and established 30 demonstration sites on pasture development and support 60 small ruminant farmers to establish pasture in their backyard.

- Database OF MSMEs Updated.

- Stakeholder engagement to develop Integrated strategic Tourism for the municipality was commenced with huge participation By GTA,GMMTB,KAKUM,ELMINA CASTLE ADMINISTRATION,MPCU,UCC TOURISM DEPARTMENT

## 2.5 EVALUATIONS CONDUCTED; THEIR FINDINGS AND RECOMMENDATIONS

Evaluations are conducted primarily to improve decision making, resource allocation and accountability. It also provides management with the performance of a project. The District however, did not conduct any evaluation on projects implemented during the period under review.

| Name of the Evaluation | Policy/programme/project involved | Consultant or resource persons involved | Methodology used | Findings | Recommendation |
| --- | --- | --- | --- | --- | --- |
| 1. Ex-Ante evaluation of physical projects | Construction of physical projects including: - Water Facilities – Boreholes - Education Facilities- KG classroom block,6-unit Classroom block and 3 Unit Classroom block, - Health Facilities –CHPS, - Sanitation Facilities – Communal Toilet Facilities | - Municipal Co-Ordinating Director - Municipal planning Officer - Municipal Finance Officer - Municipal Health Director - Municipal Education Director - Assembly Members - Municipal Chief Executive - Municipal Works Engineer - Municipal Budget Analyst - Municipal Director Of Agric | - Field Surveys including Data Collection and Analysis - Observations - Presentations - Dissemination - Report Writing | - Low access to quality healthcare - Low access to potable water - Low access to improved sanitation facilities - Low students’ attendance to school | - Provision of Health Facilities (CHPS) to increase access to quality healthcare - Provision of water facilities (boreholes and mechanised boreholes) to improve access to potable water - Provision of conducive environment for teaching and learning (Classrooms,) to improve conduct hours and student’s attendance |

Table 10: EVALUATIONS CONDUCTED

## 2.6 PARTICIPATORY M & E APPROACHES USED AND THE RESULT

The Assembly were able to organize 2 Quarterly monitoring of projects and no M&E Review meetings were conducted. However, the MPCU during the period under review could not employ any of the PM&E recognized methods such as Participatory Rural Appraisal, Citizen Report Card, Community Score card and Participatory Expenditure Tracking surveys.

Table 11: PM&E CONDUCTED

| s/n | Name of the Evaluation | Policy/programme/project involved | Consultant or resource persons involved | Methodology used | Findings | Recommendations |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Impact of support to Persons with Disability | Procurement of economic enhancement items for PWDs | Director, Social Welfare and Community Development & Municipal Planning officers | Questionnaire | - Persons who were provided with fully stocked kiosks could not sustain the business | Business management training should be given to such persons |
| 2 | Impact of school feeding on academic performance | School feeding programme | Municipal Planning officers & MED statistician | Stakeholder consultation | Improvement in academic performance is not directly linked to the programme | The programme should however continue since food hygiene and nutrition is important for learning |

# 3.0 THE WAY FORWARD

## 3.1 Key issues addressed and those yet to be addressed

Key issue(s) addressed

- Market sanitation issues were addressed with the erection of overhead tank and water connection to six (6) markets and one (1) lorry park

- Completion of most ongoing physical projects.

Issue(s) not addressed

- Renovation/Rehabilitation of dilapidated school infrastructure Municipal wide.

- Poor roads network continues to pose serious challenge which affect mobility and interconnectivity of goods & services

- Functionality of the Zonal Councils has been a challenge and effective strategies has been mapped out to ensure its viability in generation of revenue and decentralized participation.

- Inadequate extension and veterinary staff in the municipality to enhance capacities of farmers to enhance agricultural development in the Municipality

3.2 Recommendations

The Assembly recommends:

- Tapping and expanding revenue nets and increase collection rate to boost Internally Generated Funds (IGF) of the Assembly to furnish most programmes/projects prioritized but not implemented due to the delay of GOG in-flows

- Drilling/Rehabilitation of dilapidated water & school facilities is prioritized to be considered in the 2020 fiscal year

- Reshaping/rehabilitation of most feeder/Urban roads to enhance & trickle growth in the municipality

KOMENDA-EDINA-EGUAFO-ABREM MUNICIPAL ASSEMBLY

In case of reply the

number and date of this

letter should be quoted

REPUBLIC OF GHANA								         KEEA

P. O. Box 29

Tel:   233-03321-40049/03321-40028-40049				                                 Elmina – Ghana

Fax:  03321-40049/03321-40028

My Ref. No: ……………………………….						               14th  January, 2021

Your Ref. No. ……………...							               www.keeama.gov.gh

info@keeama.gov.gh		SUBMISSION OF ANNUALPROGRESS REPORT FOR 2020

I write to submit forthwith the Annual Progress Report on the District Development Programmes/Projects for the 2020 Annual Fiscal year.

Accept for your documentation, please.

Thank you.

Counting on your usual co-operation.

(DANIEL OSEI-ASIBEY)

MUNICIPAL COORDINATING DIRECTOR

For: MUNICIPAL CHIEF EXECUTIVE

REGIONAL MINISTER

CENTRAL REGIONAL COORDINATING COUNCIL

CAPE COAST

CC:

REGIONAL ECONOMIC PLANNING OFFICER

REGIONAL COORDINATING COUNCIL

CAPE COAST.

NATIONAL DEVELOPMENT PLANNING COMMISSION

NO. 13, SWITCHBACK ROAD

CANTONMENTS, ACCRA